## EXPIDITED TIMETABLE
Neighbourhood Plan stage | Tasks | Parish Council | Input from AP | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
Before you start | Formally agree to proceed | Parish Council - formal agreement | bar: 1
| Prepare initital publicity material announcing that NDP will proceed and invite community to attend | Parish Clerk working with AP | AP to provide suggested wording | bar: 2
| Despatch invitations two weeks before event | Parish Clerk | bar: 2
| First public meeting to launch and SWOT/Vision/Neighbourhood area boundary/Volunteers | Parish Council to host evening or Saturday meeting, 3 hours, | AP to design and facilitate session | bar: 5
| Report of first meeting | Parish Council to consider report | AP to prepare a report of the outcome of the first meeting | bar: 6
Neighbourhood Area | PC to apply for Neighbourhood Area | Parish Clerk working with AP | AP to provide suggested wording | bar: 5
LPA to agree Neighbourhood Area | bar: 10
Meet with LPA | PC to meet with LPA to agree terms | Parish Council and Clerk | AP in attendance | bar: 15
Neighbourhood Forum | PC to act as Qualifying Body | Full Council to creat a Steering group | bar: 7
| First meeting of Steering Group | First meeting to agree consitutution, roles and timetable | Chair of meeting to be established, supported by AP who will guide them through all actions | bar: 8
| Agree Forum Consitution based on template | Special meeting of steering group to agree consitution (or by email) | AP to prepare with input from Clerk for agreement | bar: 10
| Submit application to LPA | Clerk to submit all necessary paperwork to LPA | bar: 11
LPA tp agree Neighbourhood Forum | bar: 15; 20
Consultation and engagement Strategy | Forum to undertake stakeholder analysis | Second meeting of steering group to agree key stakeholders | Facilitated by AP | bar: 12
| Agree consultation and engagement strategy | Second meeting to agree engagement Strategy | Facilitated by AP | bar: 12
| Set up website pages | Clerk or Steering Group member | Suggested wording from AP | bar: 13 to 14
| Leaflet all houses to invite to Vision and openig event, possible survey to all households as well | Clerk to prepare leaflet, print, ensure distribution to all homes, book venue, organise catering, AV equipment | bar: 13
Vision and kick-off event | hold event for entire village | Steering Group to support | AP to prepare with input from | bar: 16
Second event to mop up? | bar: 17
Work the Kingshill school? | bar: 17
First draft vision | Prepare report on consultation results | Steering Group to consider recommendations | AP to prepare draft report with recommedations | bar: 18
| Prepare Vision | Steering Group to consider recommendations | AP to prepare draft Vision and Objectives report | bar: 18
| post on website and send emails to stakeholders | Steering Group and Clerk to send draft Vision and Objectives to all stakeholders asking for comments | bar: 19
Evidence gathering | Review existing policies and evidence | Steering Group to look for local information | AP to review LPA and other published info | bar: 17 to 18
| Site selection | Steering group to contact local landowners to identify sites | AP to advise and intervene as necessary | bar: 18 to 19
| Identify policy gaps and where additional evidence is required | Steering group meeting to discuss data gaps and agree where consultants required | bar: 18 to 19
| prepare tender briefs |  | AP to prepare tender briefs | bar: 19
| go out to tender | Set up tender interview | AP to manage tender process | bar: 20 to 22
| Seek Locality Grant funding | Clerk to apply for funding | bar: 23 to 27
Commission consultants | Commission consultants | Steering Group to Commission Consultants | AP to project manage | bar: 23
| Work with consultants | Steering Group to support | AP to support | bar: 23 to 28
| Consultants draft report | First draft report by consultants discussed with Steering Group | bar: 29
| Consultants final report | Final report | bar: 31
Report with options and issues | Prepare Issues and Options report | Steering group to agree | AP to consider all evidence and prepare issues and options report | bar: 32 to 33
| Publicise Issues and Options consultation | Steering Group to invite village to issues and options meeting | bar: 33 to 35
Options and issues consultation | hold event for entire village |  | AP to design and facilitate | bar: 36
| Report on outcome of consultation event | Steering Group to comment on report and suggest content for NDP | AP to prepare report | bar: 37
First draft | First draft Neighbourhood Plan |  | AP to prepare first draft NDP | bar: 38 to 39; 41
Steering Group to commet on first draft | bar: 39 to 41
| Modify first draft NP |  | AP to prepare final draft | bar: 42
Reg 14 Consultation | Reg 14 consultation | Steering Group to start Reg 14 consultation | AP to monitor process | bar: 43 to 48
| Modifify after Reg 14 consultation | Steering Group towork with AP | AP to prepare final draft | bar: 49
| Agree final draft | Steering Group tp agree final draft | bar: 50
Submit to LPA | Prepare consultation statement | Steering Group tp prepare consultation statement | AP to finalise statement | bar: 49
| prepare basic conditions statement | Steering Group tp prepare basic conditions statement | AP to finalise statement | bar: 49
| Submit to LPA | Clerk to submit all necessary paperwork to LPA | bar: 51

## KEY
This spreadsheet shows how the Preston Neighbourhood Develoment Plan might be procued in an expited matter.
It takes no account of public or other holidays and assumes that no unplanned delays occur.
Normal activity
Public Engagement activity
Steering Group meeting